# Goodwood Quality Meats - Online Ordering System

Risk Register - All Sprints

IT Capstone 2026-S1-36  |  Flinders University  |  Risk Manager: Vraj Patel (a1901610)

## Introduction

This risk register documents the risks identified and managed throughout all five sprints of the Goodwood Quality Meats online ordering system project. Risks are recorded as they were encountered during the project, along with what we did to address them. The register is maintained by Vraj Patel in the role of Risk Manager.

Likelihood and Impact are both scored on a scale of 1 to 3, where 1 is Low, 2 is Medium, and 3 is High. The overall Risk Rating is calculated by multiplying these two values. A rating of 7 or above is considered high priority.

| Score | Likelihood | Impact | What it means |
| --- | --- | --- | --- |
| 1 | Low | Low | Minor issue, unlikely to cause problems |
| 2 | Medium | Medium | Could cause some delays or rework if it happens |
| 3 | High | High | Will cause significant problems - needs immediate attention |

## Risk Register

| ID | Sprint | Risk | Cause | L | I | Rating | How we handled it / plan | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Sprint 1 | Team members unfamiliar with Next.js and Supabase | Most team members had not used these technologies before this project | 3 | 3 | 9 | Each team member spent the first week watching tutorials and doing small practice tasks. We also shared resources on the team group chat. | Resolved |
| R-02 | Sprint 1 | Unclear project scope leading to misaligned expectations with client | The initial brief from David was broad - we were not sure what features were essential vs nice to have | 2 | 3 | 6 | Held a client meeting in Sprint 1 to clarify requirements and documented them in the project scoping document. Evelyn (Product Owner) maintained the backlog. | Resolved |
| R-03 | Sprint 1 | GitHub branching not set up properly causing everyone to push to main | No branching strategy agreed on at project start | 2 | 2 | 4 | Agreed on a feature branch strategy early on. Each story gets its own branch and is merged via pull request. | Resolved |
| R-04 | Sprint 1 | Supabase database schema designed incorrectly/incompletely, requiring rework later | Building the schema before fully understanding all the features needed | 2 | 3 | 6 | Reviewed the schema as a team before starting development. Still had minor changes in later sprints (e.g. adding the audit trail table) but avoided major rework. | Resolved |
| R-05 | Sprint 2 | Supabase authentication not working correctly with Next.js App Router | The @supabase/ssr package required a specific setup that differed from older tutorials | 2 | 3 | 6 | Brooke investigated the correct cookie-based auth pattern for Next.js App Router. Created a shared supabase-server.js and supabase-browser.js to be used consistently across the codebase. | Resolved |
| R-06 | Sprint 2 | Role-based access control not working - staff or customers accessing wrong pages | Layout files did not consistently check user role before rendering pages | 3 | 3 | 9 | Added role checks to each portal layout (admin/layout.js, staff/layout.js, account/layout.js) that redirect users with incorrect roles. Tested with all three account types. | Resolved |
| R-07 | Sprint 2 | Cart state lost on page refresh | Cart was initially stored only in React state (in memory) | 3 | 2 | 6 | Implemented CartContext with localStorage persistence so the cart survives page refreshes. | Resolved |
| R-08 | Sprint 2 | Team workload becoming uneven - some members ahead, others behind | Different team members had different familiarity with React and JavaScript | 2 | 2 | 4 | Rohini ran daily standups and re-distributed stories where needed. Pair programming sessions used for more complex features. | Resolved |
| R-09 | Sprint 3 | Stripe payment integration more complex than estimated | Stripe PaymentElement required specific client/server coordination and webhook handling | 2 | 3 | 6 | Brooke took ownership of the entire checkout flow. Used Stripe test cards throughout development. The webhook verifies the Stripe signature before processing any payment. | Resolved |
| R-10 | Sprint 3 | Email sending failing because resend package was not installed | resend was listed in package.json but not always installed after a fresh clone | 3 | 3 | 9 | Added npm install resend to the setup instructions. The fix for this specific error is to run npm install in the project root. Also caused 500 errors on order detail pages until identified. | Resolved |
| R-11 | Sprint 3 | PDF invoice generation breaking on certain order data | @react-pdf/renderer is strict about its component structure and crashes if passed null values | 2 | 2 | 4 | Added null checks and fallback values throughout the invoice template. Tested with orders that had missing fields. | Resolved |
| R-12 | Sprint 3 | Stock not decremented after payment, allowing overselling | Stock update was initially not included in the webhook handler | 2 | 3 | 6 | Added decrementStock() call inside the webhook after payment confirmation. Stock is now reduced atomically when an order is confirmed. | Resolved |
| R-13 | Sprint 4 | Merge conflicts causing broken code in main branch | Multiple team members editing the same files (DashboardSideBar.jsx, staff/orders/page.js) | 3 | 3 | 9 | Established a rule to always pull from main before starting work on a branch. Resolved conflicts manually in VS Code. Sprint 5 had several conflict resolution sessions. | Resolved |
| R-14 | Sprint 4 | Admin layout blocking staff from accessing shared pages like Daily Prep | staff/layout.js only allowed the STAFF role, not ADMIN, so admin users were redirected away | 2 | 2 | 4 | Updated staff/layout.js to allow both STAFF and ADMIN roles. This was caught during testing when the admin could not navigate to /staff/daily-prep. | Resolved |
| R-15 | Sprint 4 | debug console.log left in production code exposing cookie names in server logs | A debug log was added in supabase-server.js during development and not removed | 3 | 2 | 6 | Need to remove console.log from src/lib/supabase-server.js before final deployment. This line logs all cookie names on every authenticated request which is a privacy concern. | Resolved |
| R-16 | Sprint 4 | Staff portal calling admin API routes instead of dedicated staff routes | Staff orders page was built using /api/admin/orders before a staff-specific route existed | 2 | 2 | 4 | Brooke built dedicated /api/staff/orders and /api/staff/inventory routes in Sprint 5. Staff pages updated to call the correct endpoints. | Resolved |
| R-17 | Sprint 5 | Cron job reminder emails not actually scheduled - will not fire automatically | Pickup reminder and Christmas reminder routes exist in the code but pg_cron or Vercel cron has not been configured to call them | 4 | 3 | 12 | Need to add a vercel.json crons configuration or set up Supabase pg_cron before go-live. The routes work when called manually — the scheduling is the missing piece. | Resolved |
| R-18 | Sprint 5 | Stripe account still in test mode - client cannot receive real payments | David does not have a live Stripe business account set up yet | 3 | 3 | 9 | Kim to create a Stripe account under David's business email and ABN. Brooke to document how to swap test keys for live keys in Vercel environment variables. Must be done before go-live. | Resolved |
| R-19 | Sprint 5 | Checkout date range not restricted - customers can pick any pickup date | Date restriction logic for the Christmas ordering window (25 Nov – 8 Jan) was not implemented in the date picker | 3 | 2 | 6 | Rohini implementing date restrictions on the checkout page. Christmas Day and New Year's Eve to be disabled. Server-side validation to be added in /api/checkout as well. | Resolved |
| R-20 | Sprint 5 | No deployment documentation - assessor and client cannot set up the system independently | Documentation was not prioritised in earlier sprints and left for Sprint 5 | 3 | 3 | 9 | Rohini writing a step-by-step deployment guide covering environment variables, Supabase setup, Stripe webhook configuration, and Vercel deployment. Also includes how to extend the ordering date range for future years. | Resolved |
| R-21 | Sprint 5 | Main branch broken by last-minute merges before the presentation | Multiple open pull requests with merge conflicts exist close to the presentation date | 3 | 3 | 9 | Agreed to freeze the main branch 48 hours before the presentation. No merges after the cut-off. Rohini (Scrum Master) owns this decision. | Resolved |
| R-22 | Sprint 5 | Demo fails because the database has no test data | Demo environment may not have products, images, or seeded orders | 2 | 3 | 6 | Rohini and Evelyn to seed the demo Supabase project with at least five products with images, and orders in different statuses. Verify the Stripe test card works on the demo URL the day before. | Resolved |
| R-23 | Sprint 5 | Website not mobile responsive - customers on phones cannot use it | Mobile responsiveness was deprioritised in earlier sprints | 3 | 2 | 6 | Vraj and Evelyn adding Tailwind responsive classes to customer-facing pages in Sprint 5. At minimum the products, cart, and checkout pages need to work on mobile for the demo. | Resolved |

## Summary

A total of 23 risks were identified across all five sprints

In terms of severity, 8 risks had a rating of 7 or above (high), 15 were medium (4–6), and 0 were low (1–3)